## Project Plan
ID | WBS | Task | Duration (wd) | Start | Finish | Predecessors | Gate / waiting on | Responsible (R) | Supporting | Notes | % Complete
1 | 1 | PHASE 0 — Initiation, funding, procurement & staffing |  | 2026-08-17 | 2027-03-05 |  |  |  |  | Mobilisation is the long pole | 0%
2 | 1.1 | Project charter & scope approved (4 connectors) | 10 | 2026-08-17 | 2026-08-28 |  |  | Platform Lead & Architect | Sponsor/Business | Salesforce connector DEFERRED — BDH carries Salesforce data | 0%
3 | 1.2 | Architecture board briefing (diagram + operator guides) | 3 | 2026-08-31 | 2026-09-02 | 2 |  | Platform Lead & Architect | Sponsor/Business | Architecture as delivered: ONE shared Connector.Chassis project (v1.18.0) referenced by all five connectors; 9 of 23 chassis modules fully shared, 67 declared per-connector divergences (see 8.5) | 0%
4 | 1.3 | Funding & FTE plan approved (finance committee cycle) | 15 | 2026-08-31 | 2026-09-21 | 2 | BANK RESOURCE | Sponsor/Business | Platform Lead & Architect |  | 0%
5 | 1.4 | Procurement: SOW/PO for external services (contractor cover) | 20 | 2026-09-22 | 2026-10-20 | 4 | BANK RESOURCE | Procurement | Platform Lead & Architect | Interim dev capacity until hire lands | 0%
6 | 1.5 | Requisition approval — Senior .NET Engineer | 10 | 2026-09-22 | 2026-10-05 | 4 | BANK RESOURCE | HR / Recruitment | Platform Lead & Architect |  | 0%
7 | 1.6 | Sourcing + interviews (.NET hire) | 30 | 2026-10-06 | 2026-11-18 | 6 | BANK RESOURCE | HR / Recruitment | Platform Lead & Architect |  | 0%
8 | 1.7 | Offer accepted + notice period served | 45 | 2026-11-19 | 2027-02-19 | 7 | BANK RESOURCE | HR / Recruitment |  | Typical 2-3 month notice | 0%
9 | 1.8 | New-hire onboarding + system access | 10 | 2027-02-22 | 2027-03-05 | 8 | BANK RESOURCE | HR / Recruitment | DevOps/Windows Engineer |  | 0%
10 | 1.9 | Internal staff released: 2 Ops Analysts + QA agreed with line managers | 10 | 2026-09-22 | 2026-10-05 | 4 | BANK RESOURCE | Platform Lead & Architect | Sponsor/Business |  | 0%
11 | 1.10 | Ops/QA access provisioning + onboarding | 10 | 2026-10-06 | 2026-10-20 | 10 | BANK RESOURCE | Ops Analysts | DevOps/Windows Engineer |  | 0%
12 | 1.11 | Source-system liaisons + backups formally named (4 systems) | 10 | 2026-08-31 | 2026-09-14 | 2 | BANK RESOURCE | Platform Lead & Architect | Sponsor/Business | Clarizen, Seismic, Altrata, BDH | 0%
13 | 1.12 | InfoSec engagement: intake form + review slot in queue | 10 | 2026-08-31 | 2026-09-14 | 2 | SECURITY GATE | InfoSec | Platform Lead & Architect |  | 0%
14 | 1.13 | DPO engaged — Altrata DPIA opened | 5 | 2026-09-15 | 2026-09-21 | 12 | SECURITY GATE | DPO/Compliance | Platform Lead & Architect |  | 0%
15 | 1.14 | CAB onboarding: change templates + calendar slots | 3 | 2026-08-31 | 2026-09-02 | 2 | CAB / CHANGE | Change Manager / CAB | Platform Lead & Architect |  | 0%
16 | 2 | PHASE 1 — Foundations: tenant, infrastructure, security reviews |  | 2026-08-31 | 2026-12-02 |  |  |  |  | Parallel tracks, queue-bound | 0%
17 | 2.1 | Dev/test M365 tenant access request (platform team queue) | 10 | 2026-08-31 | 2026-09-14 | 2 | BANK RESOURCE | M365 Platform Team | M365/Graph Engineer |  | 0%
18 | 2.2 | App-registration requests approved (4 apps, platform queue) | 10 | 2026-09-15 | 2026-09-28 | 17 | BANK RESOURCE | M365 Platform Team | M365/Graph Engineer | One app per connector | 0%
19 | 2.3 | App registrations + admin consent executed | 3 | 2026-09-29 | 2026-10-01 | 18 |  | M365/Graph Engineer | InfoSec |  | 0%
20 | 2.4 | PKI: certificate credentials issued (CA queue) | 15 | 2026-10-02 | 2026-10-23 | 19 | BANK RESOURCE | PKI Team | M365/Graph Engineer |  | 0%
21 | 2.5 | Key Vault set up + secrets loaded | 5 | 2026-10-26 | 2026-10-30 | 20 |  | M365/Graph Engineer | DevOps/Windows Engineer |  | 0%
22 | 2.6 | Dev/test Windows Server VMs (infrastructure request queue) | 15 | 2026-09-22 | 2026-10-13 | 4 | BANK RESOURCE | Infrastructure Team | DevOps/Windows Engineer |  | 0%
23 | 2.7 | Prod VMs — active-active HA pair (infrastructure queue) | 15 | 2026-10-14 | 2026-11-03 | 22 | BANK RESOURCE | Infrastructure Team | DBA |  | 0%
24 | 2.8 | gMSA + service accounts (identity team queue) | 15 | 2026-10-14 | 2026-11-03 | 22 | BANK RESOURCE | Identity Team | DevOps/Windows Engineer |  | 0%
25 | 2.9 | Firewall egress change requests submitted (4 sources + Graph) | 15 | 2026-09-15 | 2026-10-05 | 12 | BANK RESOURCE | Network Engineer | Platform Lead & Architect |  | 0%
26 | 2.10 | Firewall egress implemented + verified | 5 | 2026-10-06 | 2026-10-13 | 25 |  | Network Engineer | DevOps/Windows Engineer |  | 0%
27 | 2.11 | Proxy / TLS-inspection CA bundles distributed | 5 | 2026-10-14 | 2026-10-20 | 26 |  | Network Engineer | DevOps/Windows Engineer |  | 0%
28 | 2.12 | Webhook inbound exposure review (security) | 10 | 2026-10-06 | 2026-10-20 | 25 | SECURITY GATE | InfoSec | Network Engineer | Clarizen + Seismic listeners | 0%
29 | 2.13 | Webhook inbound rules implemented | 5 | 2026-10-21 | 2026-10-27 | 26,28 |  | Network Engineer |  |  | 0%
30 | 2.14 | SQL Server instance + DBs scheduled (DBA queue) | 10 | 2026-10-14 | 2026-10-27 | 22 | BANK RESOURCE | DBA | DevOps/Windows Engineer |  | 0%
31 | 2.15 | State DBs built + backup jobs proven | 5 | 2026-10-28 | 2026-11-03 | 30 |  | DBA | DevOps/Windows Engineer |  | 0%
32 | 2.16 | SIEM onboarding request (queue) | 15 | 2026-10-14 | 2026-11-03 | 22 | BANK RESOURCE | InfoSec | Ops Analysts |  | 0%
33 | 2.17 | SIEM ingestion + detection rules live | 5 | 2026-11-04 | 2026-11-10 | 32 |  | InfoSec | Ops Analysts |  | 0%
34 | 2.18 | Grafana dashboards + alert rules imported (ops/) | 3 | 2026-10-14 | 2026-10-16 | 22 |  | DevOps/Windows Engineer | Ops Analysts |  | 0%
35 | 2.19 | CI/CD live: runners, signing, SBOM (interim contractor) | 10 | 2026-10-21 | 2026-11-03 | 5 |  | .NET Engineer (interim contractor) | DevOps/Windows Engineer | NOT STARTED — no release pipeline exists at the repository root today; the SBOM/signing/MSI designs sit in five per-connector workflow files GitHub never runs, and no release or tag has ever been produced | 0%
36 | 2.20 | Architecture Review Board submission | 3 | 2026-09-03 | 2026-09-08 | 3 | CAB / CHANGE | Platform Lead & Architect |  | TOGAF concerns 3-7 from the architecture assessment are still open at submission | 0%
37 | 2.21 | ARB approval (board cycle) | 1 | 2026-09-30 | 2026-09-30 | 36FS+15 | CAB / CHANGE | Change Manager / CAB | Platform Lead & Architect |  | 0%
38 | 2.22 | ARB conditions closed out | 5 | 2026-10-01 | 2026-10-07 | 37 | CAB / CHANGE | Platform Lead & Architect |  |  | 0%
39 | 2.23 | Fleet threat-model pack submitted (4 connectors) | 3 | 2026-10-02 | 2026-10-06 | 13,19 | SECURITY GATE | Platform Lead & Architect | InfoSec |  | 0%
40 | 2.24 | Threat-model review (security queue + review) | 10 | 2026-10-29 | 2026-11-12 | 39FS+15 | SECURITY GATE | InfoSec | Platform Lead & Architect |  | 0%
41 | 2.25 | Threat-model findings remediated | 10 | 2026-11-13 | 2026-11-27 | 40 | SECURITY GATE | .NET Engineer (interim contractor) | InfoSec |  | 0%
42 | 2.26 | Threat-model sign-off | 3 | 2026-11-30 | 2026-12-02 | 41 | SECURITY GATE | InfoSec |  |  | 0%
43 | 2.27 | MILESTONE — Foundations complete | 0 — milestone | 2026-11-12 | 2026-11-12 | 21,23,24,27,29,31,33,34,35,38 |  | Platform Lead & Architect |  |  | 0%
44 | 3 | PHASE 2A — Wave 1 pilot: Seismic |  | 2026-09-15 | 2027-04-01 |  |  |  |  | Pilot proves pattern: ACL trim, pen test, CAB route | 0%
45 | 3.1 | SEI: intake + OAuth credentials + teamsite scope (queues) | 10 | 2026-09-15 | 2026-09-28 | 12 | BANK RESOURCE | Seismic Liaison | Ops Analysts | Guide §10 checklist | 0%
46 | 3.2 | SEI: No-MNE exclusion policy signed off (compliance) | 10 | 2026-09-29 | 2026-10-13 | 45 | SECURITY GATE | DPO/Compliance | Seismic Liaison | config/exclusions.json | 0%
47 | 3.3 | SEI: webhook secret + inbound URL agreed | 5 | 2026-10-28 | 2026-11-03 | 45,29 | BANK RESOURCE | Seismic Liaison | Network Engineer |  | 0%
48 | 3.4 | Test env configured; validate-config --strict green | 2 | 2026-11-13 | 2026-11-16 | 43,45 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
49 | 3.5 | E2E dev tenant: connection + schema + versioned crawl + webhooks | 10 | 2026-11-17 | 2026-12-01 | 48,47 |  | QA/Test Engineer | M365/Graph Engineer |  | 0%
50 | 3.6 | ACL trimming verified (2 differently-permissioned users) | 5 | 2026-12-02 | 2026-12-08 | 49 |  | QA/Test Engineer | Seismic Liaison | THE security proof; gates waves | 0%
51 | 3.7 | Exclusion verified — restricted item absent from index | 3 | 2026-12-02 | 2026-12-04 | 46,49 |  | QA/Test Engineer | InfoSec |  | 0%
52 | 3.8 | Version supersede / withdraw + incremental verified | 3 | 2026-12-09 | 2026-12-11 | 50 |  | QA/Test Engineer |  |  | 0%
53 | 3.9 | Soak: 2 weeks in test environment | 10 | 2026-12-14 | 2027-01-22 | 51,52 |  | QA/Test Engineer | Ops Analysts |  | 0%
54 | 3.10 | Pen test requested early (red-team diary booked at foundations) | 3 | 2026-10-14 | 2026-10-16 | 13,22 | SECURITY GATE | Pen-test Team | Platform Lead & Architect | Slot pre-booked so execution beats the blackout | 0%
55 | 3.11 | Pen test execution | 10 | 2026-12-02 | 2027-01-11 | 54FS+15,49 | SECURITY GATE | Pen-test Team | InfoSec | Test env | 0%
56 | 3.12 | Pen-test findings remediated | 10 | 2027-01-12 | 2027-01-26 | 55 | SECURITY GATE | .NET Engineer (interim contractor) | DevOps/Windows Engineer |  | 0%
57 | 3.13 | Pen-test retest + closure report | 5 | 2027-01-27 | 2027-02-02 | 56 | SECURITY GATE | Pen-test Team | InfoSec |  | 0%
58 | 3.14 | InfoSec production sign-off — pilot | 5 | 2027-02-03 | 2027-02-09 | 42,53,57 | SECURITY GATE | InfoSec | Platform Lead & Architect |  | 0%
59 | 3.15 | CAB submission — pilot | 3 | 2027-02-10 | 2027-02-12 | 58 | CAB / CHANGE | Platform Lead & Architect | Change Manager / CAB |  | 0%
60 | 3.16 | CAB approval (board cycle) | 1 | 2027-03-02 | 2027-03-02 | 59FS+10 | CAB / CHANGE | Change Manager / CAB |  |  | 0%
61 | 3.17 | Prod change window scheduled (post-blackout) | 2 | 2027-03-03 | 2027-03-04 | 60 | CAB / CHANGE | Change Manager / CAB | DevOps/Windows Engineer | No prod changes 15-Dec-26 .. 08-Jan-27 | 0%
62 | 3.18 | Prod deployment (MSI/SCCM, service, Key Vault) | 3 | 2027-03-05 | 2027-03-09 | 61,23 |  | DevOps/Windows Engineer | Ops Analysts |  | 0%
63 | 3.19 | First prod crawl + verification | 3 | 2027-03-10 | 2027-03-12 | 62 |  | Ops Analysts | M365/Graph Engineer |  | 0%
64 | 3.20 | Pilot business users validate Copilot answers | 10 | 2027-03-15 | 2027-03-26 | 63 |  | Sponsor/Business | Platform Lead & Architect |  | 0%
65 | 3.21 | Hypercare — Seismic | 10 | 2027-03-15 | 2027-03-26 | 63 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
66 | 3.22 | Ops handover: runbook walkthrough — Seismic | 3 | 2027-03-29 | 2027-03-31 | 64,65 |  | Ops Analysts | Platform Lead & Architect |  | 0%
67 | 3.23 | MILESTONE — Seismic LIVE (pilot) | 0 — milestone | 2027-04-01 | 2027-04-01 | 66 |  | Platform Lead & Architect |  |  | 0%
68 | 4 | PHASE 2B — Wave 2: Clarizen + Hadoop BDH (E2E early; prod gated on pilot) |  | 2026-09-29 | 2027-04-22 | [5 empty] | 0%
69 | 4.1 | CLZ: intake + service credentials + TDW access (queues) | 15 | 2026-09-29 | 2026-10-20 | 12,45 | BANK RESOURCE | Clarizen Liaison | Ops Analysts |  | 0%
70 | 4.2 | CLZ: webhook secret + inbound URL agreed | 5 | 2026-10-28 | 2026-11-03 | 69,29 | BANK RESOURCE | Clarizen Liaison | Network Engineer |  | 0%
71 | 4.3 | CLZ: FINANCIAL_DATA_MODE decision (governance owner) | 5 | 2026-10-21 | 2026-10-27 | 69 | BANK RESOURCE | Platform Lead & Architect | DPO/Compliance |  | 0%
72 | 4.4 | CLZ: test config + E2E (TDW crawl + webhooks) | 10 | 2026-11-13 | 2026-11-27 | 43,69,70 |  | QA/Test Engineer | .NET Engineer (interim contractor) |  | 0%
73 | 4.5 | CLZ: financial governance verified in chosen mode | 5 | 2026-11-30 | 2026-12-04 | 71,72 |  | QA/Test Engineer | InfoSec |  | 0%
74 | 4.6 | CLZ: InfoSec delta review + sign-off | 10 | 2026-12-07 | 2027-01-14 | 42,73 | SECURITY GATE | InfoSec |  |  | 0%
75 | 4.7 | CLZ: CAB submission | 3 | 2027-03-10 | 2027-03-12 | 74,62 | CAB / CHANGE | Platform Lead & Architect | Change Manager / CAB | Gated on pilot deploy success | 0%
76 | 4.8 | CLZ: CAB approval (board cycle) | 1 | 2027-03-29 | 2027-03-29 | 75FS+10 | CAB / CHANGE | Change Manager / CAB |  |  | 0%
77 | 4.9 | CLZ: prod deployment + first crawl | 5 | 2027-03-30 | 2027-04-05 | 76 |  | DevOps/Windows Engineer | Ops Analysts |  | 0%
78 | 4.10 | CLZ: webhooks live + verified | 2 | 2027-04-06 | 2027-04-07 | 77 |  | Ops Analysts | Network Engineer |  | 0%
79 | 4.11 | CLZ: hypercare + ops handover | 10 | 2027-04-08 | 2027-04-21 | 78 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
80 | 4.12 | MILESTONE — Clarizen LIVE | 0 — milestone | 2027-04-22 | 2027-04-22 | 79 |  | Platform Lead & Architect |  |  | 0%
81 | 4.13 | BDH: intake — endpoint, read-only principal, layout (Hadoop queue) | 15 | 2026-09-29 | 2026-10-20 | 12,45 | BANK RESOURCE | BDH/Hadoop Platform Team | Ops Analysts |  | 0%
82 | 4.14 | BDH: private CA bundle for WebHDFS TLS | 5 | 2026-10-21 | 2026-10-27 | 81,27 | BANK RESOURCE | Network Engineer | BDH/Hadoop Platform Team |  | 0%
83 | 4.15 | BDH: per-object filter policy workshops + sign-off | 10 | 2026-10-21 | 2026-11-03 | 81 | BANK RESOURCE | Platform Lead & Architect | Sponsor/Business | filters.json is change-controlled | 0%
84 | 4.16 | BDH: Graph connection provisioned (carries Salesforce data) | 3 | 2026-10-21 | 2026-10-23 | 19,81 |  | M365/Graph Engineer |  | Item id = Salesforce record Id | 0%
85 | 4.17 | BDH: validate-config --strict green (fail-closed guard proven) | 5 | 2026-11-13 | 2026-11-19 | 43,83 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
86 | 4.18 | BDH: E2E — filtered crawl + watermark + oversize handling | 10 | 2026-11-20 | 2026-12-04 | 82,84,85 |  | QA/Test Engineer | .NET Engineer (interim contractor) |  | 0%
87 | 4.19 | BDH: scale rehearsal (stress harness scale 3 + volume test) | 5 | 2026-12-07 | 2026-12-11 | 86 |  | QA/Test Engineer | .NET Engineer (interim contractor) |  | 0%
88 | 4.20 | BDH: InfoSec delta review + sign-off | 10 | 2026-12-14 | 2027-01-22 | 42,87 | SECURITY GATE | InfoSec |  |  | 0%
89 | 4.21 | BDH: CAB submission | 3 | 2027-03-10 | 2027-03-12 | 88,62 | CAB / CHANGE | Platform Lead & Architect | Change Manager / CAB |  | 0%
90 | 4.22 | BDH: CAB approval (board cycle) | 1 | 2027-03-29 | 2027-03-29 | 89FS+10 | CAB / CHANGE | Change Manager / CAB |  |  | 0%
91 | 4.23 | BDH: prod deployment + first filtered crawl | 5 | 2027-03-30 | 2027-04-05 | 90 |  | DevOps/Windows Engineer | Ops Analysts |  | 0%
92 | 4.24 | BDH: nightly schedule aligned to upstream sync (00:30) | 2 | 2027-04-06 | 2027-04-07 | 91 |  | Ops Analysts | BDH/Hadoop Platform Team |  | 0%
93 | 4.25 | BDH: hypercare + ops handover | 10 | 2027-04-08 | 2027-04-21 | 92 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
94 | 4.26 | MILESTONE — Hadoop BDH LIVE (Salesforce data available) | 0 — milestone | 2027-04-22 | 2027-04-22 | 93 |  | Platform Lead & Architect |  |  | 0%
95 | 5 | PHASE 2C — Wave 3: Altrata (compliance-gated) |  | 2026-09-22 | 2027-04-20 | [5 empty] | 0%
96 | 5.1 | ALT: DPIA assessment (privacy impact) | 25 | 2026-09-22 | 2026-10-27 | 14 | SECURITY GATE | DPO/Compliance | Platform Lead & Architect |  | 0%
97 | 5.2 | ALT: DPIA legal review + approval | 10 | 2026-10-28 | 2026-11-10 | 96 | SECURITY GATE | Legal | DPO/Compliance | Gate for all Altrata prod work | 0%
98 | 5.3 | ALT: intake — feed delivery, manifest, SFTP credentials (queues) | 15 | 2026-09-29 | 2026-10-20 | 12,45 | BANK RESOURCE | Altrata Feed Owner | Ops Analysts |  | 0%
99 | 5.4 | ALT: seat-list source, owner + refresh process agreed | 10 | 2026-10-21 | 2026-11-03 | 98 | BANK RESOURCE | Altrata Feed Owner | Platform Lead & Architect |  | 0%
100 | 5.5 | ALT: strict file ACLs on ledger/suppression/state dirs | 3 | 2026-11-04 | 2026-11-06 | 24,98 |  | DevOps/Windows Engineer | InfoSec | RPO-0 backup tier | 0%
101 | 5.6 | ALT: test config + E2E — feed ingest + manifest validation | 10 | 2026-11-13 | 2026-11-27 | 43,98,100 |  | QA/Test Engineer | .NET Engineer (interim contractor) |  | 0%
102 | 5.7 | ALT: seat-only ACL verified (never-everyone holds) | 5 | 2026-11-30 | 2026-12-04 | 99,101 |  | QA/Test Engineer | InfoSec |  | 0%
103 | 5.8 | ALT: DSAR drill — forget-subject + suppression + ledger verify | 5 | 2026-12-07 | 2026-12-11 | 102 |  | Ops Analysts | DPO/Compliance |  | 0%
104 | 5.9 | ALT: InfoSec + DPO production sign-off | 10 | 2026-12-14 | 2027-01-22 | 42,97,103 | SECURITY GATE | InfoSec | DPO/Compliance |  | 0%
105 | 5.10 | ALT: CAB submission | 3 | 2027-03-10 | 2027-03-12 | 104,62 | CAB / CHANGE | Platform Lead & Architect | Change Manager / CAB |  | 0%
106 | 5.11 | ALT: CAB approval (board cycle) | 1 | 2027-03-29 | 2027-03-29 | 105FS+10 | CAB / CHANGE | Change Manager / CAB |  |  | 0%
107 | 5.12 | ALT: prod deployment + first feed ingest | 5 | 2027-03-30 | 2027-04-05 | 106 |  | DevOps/Windows Engineer | Ops Analysts |  | 0%
108 | 5.13 | ALT: DSAR intake process ratified (ops rota + DPO countersign) | 5 | 2026-12-14 | 2027-01-14 | 103 |  | Platform Lead & Architect | DPO/Compliance |  | 0%
109 | 5.14 | ALT: hypercare + ops handover | 10 | 2027-04-06 | 2027-04-19 | 107,108 |  | Ops Analysts | .NET Engineer (interim contractor) |  | 0%
110 | 5.15 | MILESTONE — Altrata LIVE | 0 — milestone | 2027-04-20 | 2027-04-20 | 109 |  | Platform Lead & Architect |  |  | 0%
111 | 6 | PHASE 3 — Operational readiness (parallel with waves) |  | 2026-11-13 | 2027-04-15 | [5 empty] | 0%
112 | 6.1 | Ops training: Common Guide + connector guides + quick-refs | 10 | 2026-11-13 | 2026-11-27 | 11,43 |  | Ops Analysts | Platform Lead & Architect |  | 0%
113 | 6.2 | Runbook drills: dead-letter, breaker, guard refusal | 5 | 2027-04-02 | 2027-04-08 | 112,67 |  | Ops Analysts | DevOps/Windows Engineer |  | 0%
114 | 6.3 | DR drill: state backup/restore exercised | 5 | 2027-04-02 | 2027-04-08 | 31,67 |  | DBA | DevOps/Windows Engineer | Altrata strict tier | 0%
115 | 6.4 | Alert-threshold tuning on live telemetry | 10 | 2027-04-02 | 2027-04-15 | 67 |  | Ops Analysts | DevOps/Windows Engineer |  | 0%
116 | 6.5 | On-call & escalation model ratified | 3 | 2026-11-30 | 2026-12-02 | 112 |  | Platform Lead & Architect | Ops Analysts |  | 0%
117 | 7 | PHASE 4 — Stabilisation, knowledge transfer & BAU |  | 2027-04-02 | 2027-05-28 | [5 empty] | 0%
118 | 7.1 | Knowledge transfer: contractor -> permanent .NET hire | 10 | 2027-04-02 | 2027-04-15 | 9,67 | BANK RESOURCE | .NET Engineer (permanent hire) | .NET Engineer (interim contractor) |  | 0%
119 | 7.2 | 30-day stability review across all four connectors | 5 | 2027-05-14 | 2027-05-20 | 110FS+15,94FS+15,80,67 |  | Platform Lead & Architect | Ops Analysts |  | 0%
120 | 7.3 | Tenant capacity & quota review vs TENANT_GOVERNANCE.md | 3 | 2027-05-21 | 2027-05-25 | 119 |  | Platform Lead & Architect | M365/Graph Engineer |  | 0%
121 | 7.4 | Decision checkpoint: revisit deferred Salesforce connector | 2 | 2027-05-21 | 2027-05-24 | 119 |  | Platform Lead & Architect | Sponsor/Business | Built + tested; deploy only if live-CRM freshness is needed | 0%
122 | 7.5 | Lessons learned + documentation refresh | 5 | 2027-05-21 | 2027-05-27 | 119 |  | Platform Lead & Architect | Ops Analysts |  | 0%
123 | 7.6 | MILESTONE — Project closure; transition to BAU (4.2 FTE) | 0 — milestone | 2027-05-28 | 2027-05-28 | 118,120,121,122 |  | Sponsor/Business | Platform Lead & Architect |  | 0%
124 | 8 | ENGINEERING BASELINE — shared-chassis consolidation delivered on main (pre-Phase 0) |  | 2026-08-11 | 2026-08-14 |  |  |  |  | Delivered before mobilisation; appended so Phase 0-4 IDs and predecessors are unchanged | 100%
125 | 8.1 | Connector.Chassis landed as a single top-level project (now v1.18.0) | 1 | 2026-08-11 | 2026-08-11 |  |  | Platform Lead & Architect |  | One project at the repository root; chassis.yml builds and packs it (testing added 14-Aug-26 — see 8.7) | 100%
126 | 8.2 | All five connectors switched to ProjectReference on the shared chassis | 2 | 2026-08-11 | 2026-08-12 |  |  | Platform Lead & Architect |  | Seismic, Clarizen, Hadoop 11-Aug-26; Salesforce, Altrata 12-Aug-26. ProjectReference to one project on disk — never a package, never a copy | 100%
127 | 8.3 | Root CI: 8 workflows — five connectors, chassis, conformance, CodeQL | 3 | 2026-08-11 | 2026-08-13 |  |  | Platform Lead & Architect |  | Build + test on ubuntu-latest AND windows-latest, plus a non-pushed Docker build per connector. Per-connector .github/ workflows are inert — GitHub runs root workflows only | 100%
128 | 8.4 | Conformance gate resolves the ProjectReference and asserts the register | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | conformance.yml self-tests, then asserts capabilities and the divergence register on every PR | 100%
129 | 8.5 | Divergence register in force — 9 of 23 modules shared, 67 declared copies | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | Salesforce 22, Clarizen 16, Hadoop 16, Altrata 13, Seismic 0, plus 9 renamed equivalents recorded. A ratchet: CI fails on an undeclared copy and on a register line whose copy no longer exists | 100%
130 | 8.6 | Alerting consolidated onto the chassis — 4 of the 5 connectors | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | Clarizen, Hadoop and Salesforce joined Seismic. Altrata keeps its own, declared: its alert payload is an operator-facing contract SIEM routing keys on | 100%
131 | 8.7 | Chassis given its own test suite — 558 tests | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | chassis.yml now tests as well as builds and packs, on both operating systems | 100%
132 | 8.8 | Environment-flag parsing unified across the fleet | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | One boolean vocabulary; a mistyped value can no longer silently flip a gate | 100%
133 | 8.9 | Altrata decision ledger — single-byte separator tamper now detected | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  |  | 100%
134 | 8.10 | Fleet suite green on both operating systems — 5,445 tests, 0 skipped | 1 | 2026-08-14 | 2026-08-14 |  |  | QA/Test Engineer |  | Chassis 558, Salesforce 1,213, Seismic 1,025, Hadoop 988, Clarizen 897, Altrata 764. Identical counts on ubuntu-latest and windows-latest | 100%
135 | 8.11 | Repository controls: branch protection on main + Dependabot security alerts | 1 | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | Both enabled 14-Aug-26. CodeQL analyses six solutions and reports ~2,029 open alerts, but gates nothing | 100%
136 | 8.12 | MILESTONE — shared-chassis consolidation complete on main (e138f11) | 0 — milestone | 2026-08-14 | 2026-08-14 |  |  | Platform Lead & Architect |  | Out of scope of this milestone and still open: release pipeline at the repository root (2.19); TOGAF concerns 3-7 (2.20); 67 declared divergences to retire | 100%

## Legend & Assumptions
Connector Programme — bank-realistic plan (v3, 4 connectors)
Plan start | 17 Aug 2026 (Phase 0 mobilisation). The delivered engineering baseline in section 8 ran 11-14 Aug 2026, ahead of it.
Computed finish | 28 May 2027 (~9.3 months)
Scope change | SALESFORCE CONNECTOR DEFERRED — likely not implemented; the Hadoop BDH connector carries the Salesforce data (nightly mirror, ~24h lag), which was its cost rationale. The code remains built/tested in the repo; a Phase-4 checkpoint (task 121) revisits it. Pilot is now SEISMIC.
Calendar — non-working time | Mon-Fri; US federal (bank) holidays: 07-Sep-26 Labor Day; 12-Oct-26 Columbus Day; 11-Nov-26 Veterans Day; 26-Nov-26 Thanksgiving; 25-Dec-26 Christmas Day; 01-Jan-27 New Year's Day; 18-Jan-27 MLK Jr. Day; 15-Feb-27 Presidents Day; 31-May-27 Memorial Day; 18-Jun-27 Juneteenth (observed); 05-Jul-27 Independence Day (observed). YEAR-END BLACKOUT 15-Dec-26 .. 08-Jan-27: nothing progresses (not just prod changes). All dates skip these. The .msproj.xml carries the same calendar as base-calendar exceptions.
Row colours | Purple = BANK RESOURCE (hiring, staffing release, infra/PKI/identity/firewall/DBA/SIEM/source-admin queues). Red = SECURITY GATE (threat model, pen test, exposure reviews, InfoSec/DPO sign-offs, DPIA/legal). Amber = CAB / CHANGE (ARB, CAB cycles, change windows). Amber bold = milestone.
Queue/lead times modelled | Finance committee 15d; procurement 20d; hiring 95d incl. notice; infra 15d; PKI 15d; identity 15d; firewall 15d; SIEM 15d; DBA 10d; M365 platform 10d; security review queue +15d; pen-test scheduling +15d; ARB +15d; CAB +10d per submission.
Dates | Forward-pass over the dependency network (FS links; 'FS+n' = n workday lag), skipping holidays + blackout. Values, not formulas — the .msproj.xml recalculates natively in MS Project.
Wave logic | Pilot Seismic proves the pattern (ACL trim, pen test, CAB route). Wave 2 (Clarizen + Hadoop BDH) and Wave 3 (Altrata) do intake/E2E in parallel with the pilot; intakes run in parallel with the pilot (staggered by team bandwidth); their CAB submissions gate on the pilot production deployment (task 62). Altrata prod additionally gates on DPIA + legal (97).
Staffing | Interim contractor covers development until the permanent .NET hire lands; knowledge transfer is an explicit Phase-4 task. FTE model: 7.4 build / 4.2 steady state.
How to open in Microsoft Project | File -> Open -> Connector_Program_Project_Plan.msproj.xml -> 'As a new project'. Gate tags ([BANK]/[SEC]/[CAB]) prefix task names; the bank calendar (holidays + blackout) is embedded.
Source documents | Operator_Guides/ (00-05), TENANT_GOVERNANCE.md, per-connector docs/ + SECURITY.md
BANK RESOURCE example
SECURITY GATE example
CAB / CHANGE example
Status at 14 Aug 2026 | The programme itself has not started — every Phase 0-4 task is 0% complete. Section 8 records the engineering work already delivered on main at commit e138f11: ONE shared Connector.Chassis project (v1.18.0) consumed by all five connectors via ProjectReference and asserted on every PR by .github/workflows/conformance.yml. Shared does not mean uniform: 9 of 23 chassis modules are fully shared and 67 per-connector copies remain, each declared in .github/conformance/divergences.tsv and enforced as a ratchet. Fleet regression suite 5,445 tests, 0 skipped, identical on ubuntu-latest and windows-latest.
Not yet delivered | No release pipeline exists at the repository root and no release or tag has ever been produced; the SBOM / Authenticode / cosign / MSI designs sit in five per-connector workflow files GitHub never runs (task 2.19 builds the real thing). TOGAF concerns 3-7 remain open (task 2.20). CodeQL runs but gates nothing. Branch protection on main and Dependabot security alerts were only switched on 14 Aug 2026.